## Slide 1: SH1 Papakura to Bombay project
Onewhero–Tuakau Community Board – 20 July 2020

## Slide 2: Strategic context
Auckland Transport Alignment Project 2018
Indicative Strategic Transport Network July 2019
SH1 Papakura to Bombay an early project in this 30-year plan.

## Slide 3: Project overview
Stage 1: Papakura to Drury includes:
  An additional (third) lane in each direction
  Interchange improvements
  A shared walking and cycling path along the northbound side
  Improved local road connections
  Wide shoulders to future-proof for public transport services.
Stage 2: Drury to new Drury South interchange, similar features
Stage 3: Drury South to Bombay, route protection only
Delivery of Stages 1 & 2 through NZ Upgrade Programme (NZUP) announced 29 January 2020.

## Slide 4: Wider context
Interface with other NZUP projects:
  Papakura to Pukekohe electrification
  Drury rail stations
  Mill Road Project
Supporting Growth Programme
  Drury local
  Future Pukekohe expressway
SH22 safety improvements
Hamilton – Auckland passenger rail service
COVID-19 Recovery (Fast-track Consenting) Bill

## Slide 5: Planning stages
Stage 1A (green - Papakura to BP service centre works within existing designation)
  consent lodged Dec 2019, granted Jun 2020
Stage 1B-1 (red - Drury interchange) lodgement late 2020
Stage 1B-2 (grey - Otūwairoa/Slippery Creek) lodgement TBC
Stage 2 (orange - Drury South) lodgement early 2021
Stage 3 (Drury South to Bombay) lodgement late 2021 – route protection only

## Slide 6: Programme update
Stage 1A – Advanced Notice closed on 3 June 2020
Tender process – Registrations of Interest to be released in July 2020
Stage 1A construction to be awarded to successful tenderer Q4 2020
Construction to start by end of 2020
Construction of Stages 1 & 2 complete by end 2025 *

## Slide 7: Design update
Drury interchange, three options being considered:
  Eastern offline option
  Western offline option
  Online option
Interface with KiwiRail and numerous utilities
Ground investigations at interchange started early July
Detailed design underway to Drury South

## Slide 8: Engagement activities
Affected landowners engagement ongoing:
  mid-late 2019
  late Aug-Sept 2020
Public engagement ~Oct 2020
Project neighbours re condition surveys and noise walls (pre-construction)
Local boards/OTCB
Key stakeholders/utilities
Mana whenua engagement

## Slide 9: Questions?

## Slide 10: SH1 Papakura to Bombay project contacts
Email: p2b@nzta.govt.nz
Website: www.nzta.govt.nz/p2b
0800 741 722 (0800 SH1 P2B)